## Mower Project
Title |  | Early Difficulty |  | Corrected Difficulty | Card #
Line follower data |  | 2 |  | 2 | 1
WiFi connection |  | 3 |  | 3 | 2
Turn motors ON |  | 2 |  | 2 | 3
Connectivity test |  | 13 |  | 13 | 4
Application mock up |  | 3 |  | 3 | 6
API structure |  | 3 |  | 3 | 7
DB structure |  | 2 |  | 2 | 8
Raspbian Install |  | 1 |  | 1 | 9
Backend architecture |  | 5 |  | 5 | 11
Application structure |  | 3 |  | 3 | 12
dataflow: export a a single data object from DAL to PL |  | 5 |  | 5 | 13
Deploy backend to cloud server |  | 5 |  | 5 | 14
Capture a picture with Raspberry PI. |  | 3 |  | 3 | 15
Bug testing/ fine-tuning for Mower code and documentation for sprint 1 |  | 3 |  | 3 | 16
Establish communication between Raspberry Pi and Arduino |  | 2 |  | 2 | 17
Create all views to mimick the UX design |  | 8 |  | 8 | 19
Database implementation |  | 8 |  | 8 | 20
Handle encoder and gyroscope data |  | 7 |  | 2 | 21
Trasition from defined loop code to communication based code |  | 2 |  | 2 | 22
Set up and implement serial protocol |  | 3 |  | 7 | 24
Establish connection between raspberry pi and backend |  | 3 |  | 3 | 25
Create functions for Google Image API |  | 8 |  | 8 | 26
Implement Pi Bluetooth |  | 2 |  | 7 | 27
Setup Bluetooth connection between application and Mower |  | 13 |  | 13 | 28
Implement dead reckoning function |  | 3 |  | 5 | 29
Fix dependency problems |  | 3 |  | 3 | 30
Store position data from Mower |  | 5 |  | 5 | 32
Visualize path from mower |  | 13 |  | 13 | 33
Change DB structure for mower - is On |  | 3 |  | 3 | 35
Implement all API-requests and posts |  | 3 |  | 3 | 36
Documentation - backend |  | 15 |  | 15 | 37
Thread solution for Pi code |  | 8 |  | 8 | 38
Document code in Arduino |  | 2 |  | 2 | 39
Document code in Pi |  | 2 |  | 2 | 40
Mower: Software Design Description |  | 2 |  | 2 | 41
Complete system test |  | 8 |  | 8 | 43
Get Pi start script working |  | 1 |  | 2 | 44
Create utility draw class |  | 13 |  | 13 | 45
Fetch location api requests |  | 3 |  | 3 | 46
Fetch and set status to manual driving |  | 3 |  | 3 | 47
Send commands to mower from the app through bluetooth 3p |  | 3 |  | 3 | 48
ApiStructure |  | 1 |  | 1 | 49
| Sum: | 200 | Sum: | 207

## Archived Mower Project
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
TODO | [archived] REST API validation 5p | [5 empty] | 5 | https://trello.com/c/QwiaCgw8
TODO | [archived] Manage sensor interrupt | difficulty: 1 |  |  |  |  | 23 | https://trello.com/c/zYYIjSYz
TODO | [archived] Bluetooth connection for application | [5 empty] | 31 | https://trello.com/c/4kiixVHl
TODO | [archived] Connect and control mower via bluetooth | [5 empty] | 34 | https://trello.com/c/Dqg1vft4